## Sheet1
Ref | Requestor | Change owner | Procedure | Date requested | Date Ack'd | Details | Status | Date approved or rejected | Priority | Target draft completion rate | Comments | Original draft completion date | Date drafted | Date agreed | Date implemented
CR015 | Mary June | Tony S. | QMS procedure No. 12 | 2022-08-05 | 2022-08-07 | Changes to reminder letter sent about filing deadlines | Approved | 2022-08-26 | Medium | See comments | 11 Sep: On holding pending consultation with parties. 05 Nov: Consultation completed | 2022-09-06 | 2022-11-10 | 2022-01-26 | 2022-12-15